## Slide 1: Project Definition Study Workshop Kick-off
INTESA SANPAOLO
FINREP on RRH · WO 00017527 / PO 7200257892 · Confidential

## Slide 2: Today
AGENDA
Confirm the signed study, align on how we will run the workshops, and lock the plan through 31 December 2026.
Context and journey so far
Objectives and PDS deliverables
Scope, workstreams and approach
Workshop series for the rest of 2026
Team, governance and way of working
Inputs needed and decisions today
01
02
03
04
05
06

## Slide 3
From pre-kick-off
to signed study
01 Context

## Slide 4: How we got here
CONTEXT
Three steps that frame today’s workshop kick-off.
01 Pre-kick-off
02 Implementation proposal
03 Signed work order
July 2026
Aligned on PDS objectives, two workstreams, governance and a milestone proposal through year-end.
October 2026
RRH multi-country rollout proposal for Priority 1 branches — Amsterdam FINREP as the pilot driver.
Signed October 2026
WO 00017527: Project Definition Study and RRH data model analysis. Valid until 31 December 2026.

## Slide 5: Why this study matters now
CONTEXT
The PDS de-risks the multi-country RRH programme before build starts.
Programme context
What this study unlocks
Amsterdam FINREP obligation sunsets in September 2027.
Priority 1 branches proposed on RRH / Rcloud with one central RGD.
Frankfurt already live on RRH — reusable groundwork for other branches.
2027 budget and engagement model still to be confirmed.
Clear scope, constraints and migration strategy.
FINREP data requirements mapped to the RRH data model.
Gaps, risks and high-level implementation roadmap.
A shared baseline for the subsequent implementation work order.

## Slide 6
What the study
must produce
02 Objectives & deliverables

## Slide 7: Project objective
OBJECTIVES
Define the target FINREP-on-RRH migration project and assess the RRH data model to establish scope, migration strategy, risks and a high-level implementation roadmap.
Approach
A structured, workshop-based discovery designed to minimise uncertainty before the multi-country implementation begins.
Success looks like
• Shared Project Definition Document signed by both parties
• Data mapping document for FINREP requirements on the RRH / RGD model
• Agreed gaps, ownership and recommended next steps into 2027
Discovery / assessment / definition · 7 September – 31 December 2026

## Slide 8: Two documents from the signed study
DELIVERABLES
Everything else is outside this work order and will follow a separate engagement.
Project Definition Document
Scope definition
High-level functional and non-functional requirements
Architecture overview
Constraints, assumptions and dependencies
Migration strategy and target operating model
Risks and high-level roadmap
Data mapping document
FINREP data requirements analysis
Source-to-RRH / RGD mapping
Entity and business-object structures
Data quality considerations
Migration complexity drivers
Reporting and integration impacts

## Slide 9: In scope and out of scope
SCOPE
From Work Order 00017527 — anything not listed in-scope follows change control.
In scope
Out of scope
Project team mobilisation
Project Definition Study and Project Definition Document
Support for new RRH data model analysis
Data mapping document for FINREP on RRH
Acceptance / integration / performance / UAT testing
Source-system extraction (Intesa responsibility)
Build, configuration and go-live support
Non-regulatory reports and formal training
3rd-party software install / configuration
Post-implementation / parallel-run support

## Slide 10: Two workstreams, one outcome
WORKSTREAMS
Both run in parallel through 31 December 2026.
A. Project Definition Study
Functional scope of the migration
Stakeholder expectations
Constraints and dependencies
Initial migration strategy
Target operating model
Governance and engagement model
B. Data Model Analysis
RRH / RGD data architecture
Entity relationships and business objects
Master and transactional structures
Source-to-target mapping requirements
Data quality and complexity drivers
Reporting and integration impacts

## Slide 11
How we will work
through year-end
03 Workshop series

## Slide 12: Workshop-based Project Definition Study
APPROACH
Proven pattern from prior PDS engagements: short focused sessions, documented outcomes, iterative refinement.
01 Discover
02 Define
03 Analyse
04 Recommend
Current state, products, volumes, source landscape and stakeholder expectations.
Target FINREP-on-RRH scope, architecture overview and operating model.
RGD structures, source samples, mapping and gap analysis.
Risks, effort drivers and the baseline for the 2027 implementation.

## Slide 13: Path to 31 December 2026
PLAN
Milestone | Target | Focus
Workshop kick-off | 7 Sep | Teams, plan, inputs, working agreements
Discovery completed | 18 Sep | Current landscape, stakeholders, expectations
Current-state assessment | 9 Oct | Products, volumes, processes, constraints
Target application review | 16 Oct | RRH / Rcloud, FINREP coverage, TOM
RRH data model assessment | 6 Nov | RGD structures, entities, local flavours
Source data review | 27 Nov | SIRE samples, formats, quality, delivery
Gap analysis completed | 15 Dec | Mapping gaps, ownership, complexity
Final recommendations | 18 Dec | Definition pack, risks, 2027 next steps

## Slide 14: Workshop catalogue
WORKSHOPS
Workshop | Topics | Audience
PM / Governance | Roles, RAID, cadence, sign-off, engagement model | PMs + sponsors
Discovery | Business model, entities, FINREP scope, expectations | Business + delivery
Current state | Source systems, processes, known issues, constraints | Business + IT
Target application | RRH capabilities, Rcloud, FINREP coverage, TOM | Business + architecture
Data model | RGD overview, entities, master/transactional data | Data + functional
Source & mapping | SIRE dictionary, samples, source-to-RGD mapping | Data + SI / ETL
Gaps & wrap-up | Gap register, risks, recommendations, next WO | All stakeholders

## Slide 15: What we will cover in the sessions
WORKSHOPS
Indicative agenda building blocks — refined per workshop invite.
Discovery
Current state
Target application
FINREP scope and first reporting date
Products, counterparties, volumes
Stakeholder expectations
SIRE and related sources
Existing FINREP process
Known limitations and manual work
RRH / Rcloud walkthrough
Map-once, report-many model
Target operating model options
Data model
RGD core vs local flavours
Business objects and relations
Module relevance for FINREP
Source & mapping
Data dictionary and samples
File formats and cut-offs
Draft source-to-RGD mapping
Gaps & wrap-up
Gap and risk register
Ownership matrix
Recommendations into 2027

## Slide 16
Who delivers
and how
04 Team & way of working

## Slide 17: Who is in the room
PEOPLE
Named counterparts from the work order; remaining Intesa roles to confirm today.
Regnology
Intesa Sanpaolo
Mihaela Hauca — Project Manager
Kevin Van den Bossche — delivery support
Arjan Groen
Amneris Daci
Francesco Pierobon
Georgette Ballul
Effort envelope: 104h functional · 32h technical · 24h PM.
Lorenzo Marzagalli — Project Manager
Sponsor — to name today
Business owner — to name today
Branch / FINREP SMEs — to name today
Data / SI contacts for SIRE samples
Coordinates internal stakeholders and access.

## Slide 18: Ownership matrix
GOVERNANCE
Activity | Accountable | Responsible | Contributors
Project kick-off | PM | PM | Sponsor, Business Owner
Stakeholder identification | PM | Functional consultant | Customer project team
Current-state assessment | Business Owner | Functional consultant | Customer project team
Target application review | Functional consultant | Functional consultant | Customer project team
Data model assessment | Functional consultant | Functional consultant | Customer project team
Source data review | Business Owner | Functional consultant | Customer project team
Gap analysis | Functional consultant | Functional consultant | Customer project team
Risk assessment | PM | PM & Functional | All stakeholders
Final recommendations | Sponsor | PM & Functional | All stakeholders

## Slide 19: How we will work
WORKING MODEL
Taken from the signed work order assumptions.
Remote delivery
Intesa provides
Sign-off
Cadence
Remote within business hours (09:00–17:00 local), unless otherwise agreed in writing.
People, access, documentation, environments and data in the prescribed format.
Documents and reports signed off within five business days of request.
Joint planning of workshops; RAID maintained; progress reviewed in regular PM syncs.

## Slide 20: 160 hours through 31 December 2026
EFFORT
Time & materials · Estimated Project Value €31,080 · 80% committed draw-down.
104 hours
32 hours
24 hours
160 hours
Functional consultant
Requirements, workshops, definition and mapping.
Technical consultant
Data model, architecture and technical assessment.
Project management
Plan, coordination, RAID and reporting.
Total for the study
Valid until Work Order Expiry Date: 31 Dec 2026.

## Slide 21
What we need
to start
05 Inputs & decisions

## Slide 22: What we need from Intesa
INPUTS
So discovery and mapping can start immediately after this meeting.
Names
Access & docs
Sample data
Sponsor
Business owner
Branch / FINREP contacts
Data and SI counterparts
Systems landscape
Existing FINREP documentation
Study / UAT environment access
Security and connectivity
SIRE data dictionary
Representative FINREP-related extracts
File formats and cut-off times
Known data-quality gaps

## Slide 23: Three agreements we need today
TODAY
Lock these so the workshop calendar can be issued this week.
01 Counterparts
02 Dates
03 First inputs
Confirm sponsor, business owner and workshop attendees for September–October.
Confirm or adjust the milestone dates from the pre-kick-off plan.
Agree owners and due dates for access, documentation and sample data.

## Slide 24: Immediate next steps
NEXT STEPS
From this kick-off into the first discovery workshops.
This week
By mid-September
Through Q4
By 31 Dec
Issue workshop calendar
Share request list for docs/data
Set recurring PM sync
Complete discovery workshops
Mobilise named SMEs
Baseline RAID log
Run assessment workshops
Iterate definition & mapping packs
Review at each milestone
Final recommendations
Signed definition & mapping
Handover into 2027 planning

## Slide 25: Let’s start the workshops
Intesa Sanpaolo · FINREP on RRH · Project Definition Study · Confidential